## Leveling
Scope item | Required? | Bidder A | A incl? | Bidder B | B incl? | Bidder C | C incl? | Plug for missing $ | Notes
Base bid (as submitted) | Yes | 0 | Y | 0 | Y | 0 | Y | 0 | Enter each bidder's number
Addenda 1–3 acknowledged | Yes |  | Y |  | N |  | Y | 0 | Example: B did not acknowledge Add. 2
Firestopping at rated walls | Yes |  | N |  | Y |  | Y | 0 | Plug value for A
Temporary power | Yes |  | Y |  | Y |  | N | 0
Bond | Yes |  | Y |  | Y |  | Y | 0
Alternate 1: LED upgrade | Alt |  | Y |  | Y |  | N | 0

## Leveled totals
Bidder | Submitted base | Plugs added | Leveled total
Bidder A
Bidder B
Bidder C
Note: Plugs are your estimate of what a missing required item costs; they are assumptions, label them in the award memo.

## How to use
Construction bid leveling template · RenderDraw
1. List every required scope item from your scope sheet, including addenda acknowledgement.
2. Mark each bidder Y (included), N (excluded) or Q (qualified).
3. Plug excluded required items to get a leveled, apples-to-apples total.
Example rows are synthetic. Replace them with your project data. All rates, prices and waste factors are editable assumptions.
Want quantities filled from your drawings with the source sheet on every row? Request a free sample takeoff: https://renderdraw.com/trial