## Checklist
# | Check | Pass? | Sheet / ref | RFI # | Notes
1 | Sheet index matches the sheets received (no missing pages)
2 | Every sheet shows the same issue date / revision as the bid set
3 | All addenda received and logged; superseded sheets marked
4 | Scales are stated and graphic scale bars measure correctly
5 | PDFs are vector or scanned at legible resolution
6 | Legend and symbol list present for each discipline
7 | Schedules (door, finish, fixture, panel, equipment) present and complete
8 | Plan tags match schedule entries (no orphans either way)
9 | Spec sections exist for every scope you are pricing
10 | Details referenced on plans exist on the detail sheets
11 | Dimensions close (overall = sum of strings) on key plans
12 | Conflicts between disciplines noted (e.g., struct vs. arch)
13 | Alternates and allowances identified on drawings and in specs
14 | Scope split between trades is clear (responsibility matrix)
15 | Existing conditions / demo scope defined

## How to use
Drawing validation checklist before estimating · RenderDraw
1. Run this before the first quantity is taken; a missing sheet found on bid day costs more than a slow start.
2. Every "No" should become an RFI or a qualification in your bid.
3. Keep the completed checklist with the bid file.
Example rows are synthetic. Replace them with your project data. All rates, prices and waste factors are editable assumptions.
Want quantities filled from your drawings with the source sheet on every row? Request a free sample takeoff: https://renderdraw.com/trial