## Read me
Preconstruction services scope checklist
RenderDraw template · renderdraw.com · Yellow cells are inputs; blue rows are calculated. Edit any default.
This is a planning checklist, not a contract and not legal advice. Use it to prepare for conversations with the owner and your attorney.
Milestones tab: estimates by design phase with expected accuracy class, format and due dates.
Scope tab: services, who provides them, and whether they are included in the precon fee.

## Scope
Category | Service / deliverable | Included? | Responsible | Notes
Estimating | Conceptual estimate at schematic design | Yes | GC
Estimating | Detailed estimate at design development | Yes | GC
Estimating | GMP or lump-sum proposal at construction documents | TBD | GC
Value engineering | VE log with cost and schedule impact per item | Yes | GC
Constructability | Constructability reviews at each milestone | Yes | GC
Schedule | Preliminary schedule and phasing plan | Yes | GC
Procurement | Long-lead item list and early release recommendations | Yes | GC
Trade input | Design-assist subcontractor input (e.g. MEP, steel, facade) | TBD | Sub
Site | Site logistics plan | TBD | GC
Fee | Precon fee basis (lump sum, hourly, credited to GMP) | TBD | Owner/GC | Discuss with attorney
Handoff | Ownership of estimates and documents if the project does not proceed | TBD | Owner/GC | Discuss with attorney
Handoff | Conditions for converting to construction contract | TBD | Owner/GC | Discuss with attorney

## Milestones
Design phase | Estimate type | Format | Due date | Status
Schematic design | Conceptual / parametric | Systems or $/sq ft |  | Planned
Design development | Detailed | CSI division summary |  | Planned
50% CDs | Detailed reconciliation | Division + VE log |  | Planned
100% CDs | GMP / bid | Trade-level buyout basis |  | Planned