## Checklist
Phase | Item | Owner | Due | Status | Notes
Documents | Confirm current drawing set, spec book and addenda list |  |  | Open
Documents | Log RFIs from takeoff with sheet references |  |  | Open
Scope | Scope sheet by trade, including exclusions and alternates |  |  | Open
Scope | Identify long-lead items and submittal requirements |  |  | Open
Estimate | Takeoff reviewed and quantities traced to sheets |  |  | Open
Estimate | Budget vs. estimate reconciliation and contingency |  |  | Open
Schedule | Baseline schedule, milestones and site logistics |  |  | Open
Site | Existing conditions survey and as-built measurements |  |  | Open
Procurement | Bid packages issued, leveled and recommended |  |  | Open
Risk | Risk register with owners and mitigations |  |  | Open
Handoff | Estimate-to-operations turnover meeting held |  |  | Open

## Meeting agenda
# | Topic | Lead | Minutes | Decisions / actions
1 | Introductions, roles and communication plan |  | 5
2 | Scope review and exclusions |  | 15
3 | Schedule, phasing and milestones |  | 15
4 | Submittals, RFIs and long-lead items |  | 10
5 | Site logistics and safety |  | 10
6 | Budget, alternates and value engineering |  | 15
7 | Open questions and next steps |  | 10
TOTAL

## How to use
Preconstruction checklist & meeting template · RenderDraw
1. Use the checklist through preconstruction; the meeting agenda for the kickoff or turnover meeting.
2. Status uses a drop-down so you can filter open items.
3. Edit phases and items to match your company process.
Example rows are synthetic. Replace them with your project data. All rates, prices and waste factors are editable assumptions.
Want quantities filled from your drawings with the source sheet on every row? Request a free sample takeoff: https://renderdraw.com/trial