## Project
Project and billing period
Project | [Project name]
Contractor | [Company]
Application # | 1
Period to
Retainage % | 10% | Per contract. Some contracts reduce retainage after 50% complete.

## SOV
Schedule of values (continuation sheet)
Not an AIA document. Columns follow the common continuation-sheet layout; match your contract's required form.
Item | Description of work | Scheduled value | Previous applications | This period | Materials stored | Completed & stored to date | % complete | Balance to finish | Retainage
1 | General conditions / mobilization | 18000 | 9000 | 3000 | 0
2 | Demolition | 12500 | 12500 | 0 | 0
3 | Framing and drywall | 86000 | 30000 | 25000 | 4000
4 | Doors, frames, hardware | 24000 | 0 | 6000 | 8000
5 | Painting | 21000 | 0 | 4000 | 0
6 | Flooring | 33500 | 0 | 0 | 12000
7 | Closeout and punch list | 5000 | 0 | 0 | 0
TOTALS

## Payment Summary
Application for payment summary
Original contract sum
Net change orders | 0
Contract sum to date
Completed & stored to date
Retainage
Earned less retainage
Less previous certificates | 0
CURRENT PAYMENT DUE
Balance to finish incl. retainage